## Sheet1
Sprint Retrospective
Liked | Learned | Lacked | Longed For
Share aspects of the sprint that you enjoyed or found particularly effective. | Discuss lessons learned, whether they are related to processes, technical aspects, or teamwork. | Identify areas where the team felt a lack of resources, support, or information. | Discuss any desires or expectations that the team had but were not met during the sprint. | Guidelines
The positive attitude and willingness to help among team members were fantastic and contributed to a great working atmosphere. | We learned from the last sprint that maintaining a balance between new features and technical debt is crucial for long-term stability. | We lacked clarity on the acceptance criteria for some user stories, resulting in misunderstandings during development. | I longed for more detailed sprint planning discussions to uncover potential risks and dependencies. | Example
Having a defined sprint goal helped in staying focused on the task. It provided a sense of purpose and clarity, reducing distractions. | Being aware of the team’s actual capacity and not overloading it ensures realistic sprint goals and prevents burnout | Team members may not have access to the required tools, licenses, or hardware to perform their tasks efficiently. | The sprint was too focused on delivery, leaving little time for skill development or professional growth.
The teamwork and collaboration during daily stand-ups and discussions were effective. Open communication allowed for quicker issue resolution and feedback exchange. | Teams need to find the right balance between ambition and feasibility. | Problems with development environments, testing servers | The scope turned out to be too large, with more tasks than the team could realistically handle. This often led to rushed work or incomplete features
The limited time frame of a sprint pushed the team to be efficient. The sense of urgency often sparked creativity and productivity. | Sometimes, a sprint doesn’t go as planned. Being flexible with the scope (adjusting it based on challenges faced) helps maintain focus on delivering quality rather than just meeting arbitrary deadlines. | Without backing from leadership, the team may feel disconnected from the larger strategic goals and find it difficult to push through blockers. | he team expected access to the necessary tools, environments, and technical support to complete their tasks smoothly.
The iterative nature of a sprint ensured that small, functional parts of the product were completed, giving a sense of achievement and progress. | Being adaptable and open to change (whether it's scope adjustment, process tweaks, or workload redistribution) helps the team navigate unexpected challenges without unnecessary stress. | Team members may feel unsupported if there is minimal interaction or guidance from senior leaders | The team hoped for better infrastructure support and resources to avoid delays caused by technical bottlenecks.